## Sheet1
Florida Training Task Force Project Boxes
Row Labels
Active
OffShore Hazmat Pilot Program
POC- Team
(blank)
Electric Vehicle Battery initiative
Chief Marshall, Chief Murphy, Chief Russo, Charlene Burke, Burt McKee, Mike Bloski, Robert Kincart, Chris Burghdurf, John Kohnke, John Gatlin, JoAnne Rice, Sam Graves, Melissa Woehle, Glen Perrigan
-Identify Best Practices 1st Responder mitigation and response for Lithium-ion fires. Explore mitigation and response to water intrusion to electric lithium ion vehicle batteries. Hurricane Ian identified a need for planning and mitigation from
Fire Fighting PFAS Foam disposal
Hazmat Team Capability Assessments
Completed
Monitoring
Assess SHGAP Assessment Process for Hazmat Team Funding
Awareness Level Training for White Powder
Develop SME Database
EPLAN Awareness and Training Materials for Responders
E-Plan Upgrade Provide Additional Detail
Maintain FLAHR / FFCA website for TTF products
Mass Technical DECON Team Capability Assessment
TTF Web Page and Project Summaries
Update SERC Guidelines for First Responder Hazmat response training
Grand Total
Alt + F5 updates table

## Project List
Project | Status | Project Type | Description | Lead | Project Documents Location
Fire Fighting PFAS Foam disposal | Active | Updates | Identify amount of PFAS fire fighting foam in Florida, explore funding and process to dispose of contaminated Foam. | Ashley Shive, Chief Knoff, John Gatlin, John Kohnke
Update SERC Guidelines for First Responder Hazmat response training | Monitoring | Updates | Hold for funding
Mass Technical DECON Team Capability Assessment | Monitoring | Updates | ​Creation of Check Off Sheet for capabilities of a Mass Decontamination Team. Project began Feb 2011 Lead: FSFC/FSM Team: Scott Chappell and FLAHR, Matt Marshall Awaiting updated technical DECON assessment from FSFC staff. DRS will work with Region III Dixie County Decon Team to establish victim capcity and develop draft check off sheet for this resource (large scall technical decon team). | POC- Scott Chappell, Matthew Marshall
Electric Vehicle Battery initiative | Active | Updates | Explore mitigation and response to water intrusion to electric lithium ion vehicle batteries. Hurricane Ian identified a need for planning and mitigation from electric car batteries sitting in water and catching fire. In addition fires caused by EV's charging under condominium homes in garages a threat. FTansportation of lithium Ion batteries in shipping containers starting fires. | Matthew Marshall
Hazmat Team Capability Assessments | Active | Updates | ​“Exploration and identification of funding methods and/or possibilities for accomplishing SERC TTF Hazardous Materials Team Type I and Type II Capability Assessments. This initiative has previously been accomplished as an HMGP project as well as through the SFM associated with SHGAP grant recipient monitoring.” Lead: DEM. Team; Matt Marshall, State Fire Marshalls Office, DEM Ongoing exploration of funding potential continues May of 2014 - Self Assessments of Hazmat Teams completed through FSFC. Results pending as of July 2014. Note: Site visits accomplished for several Hazmat Teams prior to end of 2014. Request for scheduling of remaining non-assessed state teams was relayed at 2015 FRE. Please contact Scott Chappell or Matt Marshall to facilitate agency team being schedule for site visit. Status report to SERC TTF Pending. DRS 1/21/2015 The LEPCs are now helping with gathering the self assessments. They are also assisting with site visits On going, 1st year was a succuss with collecting data. | Pat Feagle, Heather Lorimor, John Kohnke, TJ Lyons, Mike Bloski
Develop SME Database | Monitoring | Systems & Relationships | Develop a database of subject matter experts for all related hazardous materials training; SME list not completed. Lead: Dilks | POC- Frank DeFrancesco, John Kohnke, Jonathan Lamm
Chapter 556 - Underground Pipeline | Completed | Updates | ​Florida State Fire Marshalls Office | POC-John Kohnke
OffShore Hazmat Pilot Program | Active | Training |  | POC- Team
Shipboard Hazmat Response | Completed | Publications | Moved to Offshore Hazmat Pilot Program ​Create protocol and MOU for shipboard hazmat response for integrating land based Hazmat Teams with Shipboard Response Lead: Forest Willis/Chief Murphy Link to Needs Analysis Project initiated by Scott Ehlers and Chief Murphy on July 2011 10 March 9,2016 - All- I have attached a draft agenda for review and comment. It is very ambitious but I think we may be address multiple issues simultaneously. My major goal for this meeting is for the team to get to know each other and be able to put eyes-on/hands on the Coast Guard Aircraft and waterborne platforms and learn their capabilities and limitations. Policy/MOU issues will fall out later though we will briefly discuss them. The over-arching objectives are to determine 1) what we can reasonably and safely accomplish, 2) Identify mutual or individual training needs, and 3) Identify any equipment needs or considerations that need to be addressed via procurement, etc. Once we all have the "big-picture" so to speak, we can continual to refine issues by phone conferences or meetings of the State Hazardous Material Training Task Force. My hope is that we would have something at the 80-90% level ready to present to the State Emergency Response Commission and the District Commander by Fall 2016 and be ready to present the final product at the 2017 State HAZMAT Exposition. 01/21/2014: Update from Forrest Willis at TTF. Chief Murphy, Scott Elhers, Forrest Willis, and Commander from Alabama USCG met to discuss the potential of integration of non-military first response hazmat assets into the USCG off-shore response to hazmat incidents. Discussions included initial exploration into capabilities, integration of response teams, and potential MOUS. Another meeting is planned and Forrest Willis is working on coordination issues within the USCG. A recent event aboard a vessel involving a vehicle fire in cargo box may stimulate discussion within the USCG regarding benefit of such an arrangement. Forest Willis working with Military colleagues and regional responders to assemble a series of workshops to refine approach to integration of efforts. Lead: Chief Murphy Team; Chief Murphy, Scott Elhers, and Forrest Willis. | POC- Michael D. Murphy
Revision of Hazmat Training Guidelines | Completed | Training | ​Revision of SERC Public Safety Hazmat Training Recommendations with current versions of NFPA 472 & 473. Lead: Paul Wotherspoon. Team; Matt Marshall, Don Sessions, and Tim Date. 01/21/2014: Scope of Work constructed by Sessions and Marshall. Forward to Tim Date for integration. Per Paul, document has cleared legal and is making way through DEM for inclusion in Bid document to secure vendor. Timeline for deliverables is specified in Scope of Work. DEM executed contract following SC recommendations for vendor facilitated revision of Florida Hazmat Response Training Guidelines. TTF Sub-Committee for review of material includes: Scott Chappell, Butch Lodermilk, Matt Marshall, Jonathan Lamn, and Don Sessions. Selected Vendor: Lee Newsome. Contract awarded to EREC. EREC reported at Janury at FRE: First deliverable - Hazmat Tech and Recert for Hazmat Tech Check Off Sheets target draft for release by Feb 15th, 2015. Solicit any comments by members for format suggestions related to check-off sheets. Send comments directly to Lee Newsome. | POC- Matthew Marshall, Donald Sessions
Third Annual Hazmat Symposium at Fire Rescue East | Completed | Training | ​Oversight planning for the 2015 Third Annual Hazmat Educational Track at Fire Rescue East. Lead: Johnathan Lamm Team; TBA Target Date: FRE January 2015 | POC- Jonathan Lamm
Hazmat Team ICS Curriculum | Completed | Training | “Curriculum enlightening the student to the unique aspects of organizing the response to an hazardous materials incident inclusive of the functions and responsibilities of the various groups that may be created to support mitigation efforts” Project began February 2011. Lead: Don Sessions and Joe Nelson Power Point created in 2013, intergaration of risk analysis information occuring along with exploratio of alternatuive models. Status Update Needed. Target Date: Open | POC-
Supplemental Project List for EPA Funding | Completed | Funding | ​Lead: Michael Murphy Initiative to develop a list of supplemental projects by region; prioritized within each region, for the purpose of potential funding in lieu of fines for infraction of EPA regulations. 2016March January - 2016 The Website for this project and the forms to file a project have been completed by DEM staff. The site is up and running and groups or individuals need to submit projects into the statewide database. The EPA has executed the agreement and is willing to steer businesses to the list for a supplemental project as opposed to fines. Project is completed except for use by Florida based organizations. | POC-Michael D. Murphy
Oil Spill Response for Hazmat Technicians | Completed | Standards & Classification | ​Recognition of Florida Hazmat Team members to respond to Spills. Lead: Chief Murphy. Team; Chief Murphy and Forrest Willis. Working through Forrest Wilis, USCG Dist 7 01/21/2014: Project update by Forrest Willis given at TTF. Still attempting to clear hurdles. Information requested from Chief Murphy to include past correspondence regarding TTF/SERC attempt to resolve. Letter to be sent to Chief Baker requesting that they aid in facilitating Forrest WIllis efforts to develop an internet based lesson plan for responders specifically providing crude oil spill into waterways considerations and response guidelines. Target Date for resolution: Before next Incident January - 2016 The USCG has developed a course. April 2017 Still working with USCG and FFCA for port agreement | POC- Michael D. Murphy
FSFC Rule Making regarding Hazmat Certification | Completed | Standards & Classification | ​Lead: Scott Chappell @ FSFC Rule making process outlining: Educational Training Requirements for Students, Instructors, and Facilities for delivery of training. Credentialing and testing requirements will be memorialized through rule. Draft Rule language from January 2015 Fire Rescue East Meeting is attanced. Review and submitt comments directly to FSFC Bill Wentlandt. DRS 01/21/15 | Scott Chappell | https://portal.floridadisaster.org/SERC/External/Training%20Task%20Force/TTF%20Project%20Boxes/FSFC%20Rule%20Making%20regarding%20Hazmat%20Certification
Hazmat Team Marketing | Completed | Systems & Relationships | ​Exploration of methodologies for public awareness of services provided by hazmat responders throughout Florida. Lead: Chief Murphy Status Report Needed. | Michael D. Murphy
Secure portal for acess to TTF Products | Completed | Systems & Relationships | ​Find portal via Fusion Center or other to store protected information. Project began April 2011 Lead: DEM Team; John Khonke, Joe Nelson SERC Sharepoint created to address security issues. Currently working to overcome internal password issues within DEM. Status Update Required Target Date: As soon as reasonably possible. To Login go to: https://portal.floridadisaster.org/_layouts/customloginpage/login.aspx?ReturnUrl=%2f_layouts%2fAuthenticate.aspx%3fSource%3d%252F&Source=%2F • All of the logins use your e-mail address as the login name. • The password is the same e-mail address in lower case unless you’ve previously changed your password. • Users should be advised to change their password when they login for the first time. • Users can change their password by clicking on their name in the upper right corner to find the “Change Password” control. • If the users forget their password they will be asked to answer a security question when they click the “Forgot your password?” link on the login page. • The security question for new users for password retrieval is: “Why are you a member of this portal?”. • The answer to the security question is “SERC”. • The password will be mailed to the user if they (1) click “Forgot your password?”, (1) enter their e-mail address and (3) answer the security question. • All users have Read level access to the entire SERC site as members of the security group “SERC Members All”. • If the you need help send an e-mail tospadmin@em.myflorida.com (EOC-SPAdmin). Four people receive the email sent to EOC-SPAdmin. After logging in, cursor over the ribbon to “Preparedness” and choose “SERC” which appears below “Preparedness”.
Chemistry in Schools Program | Completed | Resources | ​Generated from discussion during the May 28, 2009 conference call was the idea of a web-based program offered through the chemical industry promoting interest of high school aged students in the field of Chemistry. A project box was created to follow progress of individuals interested in pursuit of this initiative. The working group explored the possibility of creating a scholarship through the use of supplemental funding which was later determined by SERC TTF council that such an endeavor could not be legally implemented. The working group continued exploring new opportunities and educational models during the following conference calls. The project was soon tabled. | Michael D. Murphy
Model Reporting System for Responders | Completed | Resources | ​Develop a model reporting tool for hazardous materials response. Project was under development from I-Chiefs fusion center. Funding was terminateds in 2012. Lead: DeFrancesco | POC- Frank DeFrancesco
Chemical Classification for Evidence | Completed | Publications | ​Project dealt with utilization of PCR technology in the field by health or hazmat. Also dealt with 20/20 assay at mail center. Health wanted all samples to go to state lab. Lead: Joe Nelson
Forth Annual Hazmat Symposium at Fire Rescue East | Completed | Training | ​Planning for the 2016 Hazmat Training Symposium at 2016 Fire Rescue East. | POC- Jonathan Lamm, Butch Loudermilk, Matthew Marshall
Revise / Create Hazmat Operations Level Capabilities Checklist | Completed | Updates | ​Group to revise/create a Hazmat Operations Level Capabilities Checklist refering to NFPA 472 and mission specific capabilities. Group to identify all potential stakeholders for input. Target within 2016. Working on RFP | POC- Butch Loudermilk, Jonathan Lamm, Matthew Marshall
Awareness Level Training for White Powder | Monitoring | Resources | “Constructed of an Awareness Level Curriculum for: first responders, public safety communicators, law enforcement, DOH laboratory personnel, and allied response partners for managing the report of a suspicious potential biological substances. This curriculum would be compatible with the DOH pending revised global document for managing such incidents as well as respective of the SERC Public Safety Sampling Guidelines for Hazardous Materials Teams previously approved by SERC. The DOH global document was approved by the RDSTF SWG in May of 2013.” Lead: DOH; Bobby Bailey/ Mike Jacobs Needs to be monitored for training Update Needed | POC-
Maintain FLAHR / FFCA website for TTF products | Monitoring | Resources | Hosting of SERC TTF Hazmat Team information on FLAHR portal assocated with FFCA website FLAHR; Marshall Update Needed | Matthew Marshall
TTF Web Page and Project Summaries | Monitoring | Resources | ​ "Display of information related to iniatives accomplished and embarked by the SERC Training Task Force is desired on the TTF web page link of the Florida Department of Emergency Managment Website. Project began February 2011 Lead: DEM Information should include; 1. Web Page Updates showing current information pertaining to SERC and TTF including meeting information, TTF products, and viable links to other resources. 2. Summary of all projects undertaken by the TTF, history, and disposition of the projects. 3. Completion of the TTF Project Database is the completion of the project" Status Update Needed
EPLAN Awareness and Training Materials for Responders | Monitoring | Publications | ​EPLAN Awareness and Training Materials for Florida Responders Lead: Matt Marshall, DEM Creation of a link on SERC TTF Web page explaining access information to Floirda responders to the E-Plan tool in use by Florida DEM. The information will also link the viewer to DEM staff that may assist in provding training reference materials (power point constructed by Matt Marshall) to aid responder software navagation. Team: Matt Marshall and DEM Staff Target Date: April 2014 | POC- Matthew Marshall
E-Plan Upgrade Provide Additional Detail | Monitoring | Updates | ​Expanded use of EPLAN capability as a response tool Lead: Chief Murphy, DEM Staff Initiative to create an informational link on SERC TTF web to contain reference materials "EPLAN Awareness and Training Aterials for Responders" opened in January 2014 | POC- Michael D. Murphy
Assess SHGAP Assessment Process for Hazmat Team Funding | Monitoring | Funding | Consider SERC TTF endorsement of or alternate recommendations to SHGAP funding process for distribution of funding to state regional teams. Lead: John Khonke Team consist of all TTF members. August 2013: Letters of support constructed by TTF to RDSTF advocating preservation of funding to all current Type I Hazmat Assests. Request for SERC support obtained, draft letter written and sent to SERC; letter sent to RDSTF. RDSTF approached and message of support shared. 10 Teams eliminated from Funding. Efforts to restore funding occuring. Note: Efforts to restore funding for 10 teams failed by one vote at Executive Funding Meeting. Target Date: 2014 Funding Cycle Statewide threat and vulnerability assessment results pending. This data may be used to assess impact of team cuts. | POC- John Kohnke